## Sheet1
EVENT CHECK LIST - Kevin Smyth updates 23 Nov 2021
Item Number | Item | Description | Lead person | Status | Action date | INFO/ OPEN/ CLOSED
| Agenda | Final agenda to be shared with Hotel, sponsors and speakers | EH |  | 2021-11-19 | INFO
| Agenda | Upload master agenda on drop box | SW |  | 2021-11-16 | INFO
| Agenda | Agenda to be updated with new sponsor - Kober | SW |  | 2021-11-16 | INFO
| Attendees | James Drinkwater PHSS invite. | SW |  | Closed | N/A
| Printing and materials | Contact names and details required for all key personnel: Committee members Presenters Delegates VIP's Sponsors Students Hotel representative | EH/KS/SW | Details to be issued to all committee members Hotel representative - on the 26th - Sean O'Neil Hotel representative on the 25th - Aga | 2021-11-19 | INFO
| Audio/Visual | ROC Laptop will be used at event, KS to provide back-up laptop. | RO'C/KS |  | 2021-11-25 | Closed
| Audio/Visual | Roving mikes - 2 x volonteers required plus back-up | AK | KS, AK, Elizabeth's support | 2021-11-09 | INFO
| Audio/Visual | Alan / Richard / Jonny - are co-ordinating and managing - AVI | AK, RO'C, JP |  | Ongoing | INFO
| Audio/Visual | Alan K to provide details of screens, mics, etc provided by AVS | AK |  | 2021-11-19 | INFO
| Covid 19 | AVS compliance | AK | Hi Alan, Yes, I can confirm that both myself and Kenneth Hynes will have Digital Covid Certs which we can display upon demand for the conference. Regards, Alan AVS Audio Visual Services Ltd. Embankment Blessington Rd. Corbally Co. Dublin Ireland D24VYE0 Ph: +353 1 4528444 Mob: +353 85 8758540 | Closed
| Audio/Visual | Follow-up with Alan Kelly - if online what do you see | AK/RO'C | Video at lunch time and sponsor slide at start and coffee breaks? Between slides - we will show the sponsors. The Sponsors slide will be at the start bbefore hand and presented between presentations. For Lunch time - the PDA video will be played for 1 hr. This video will be played onlne / remote and in the room. | 2021-11-19 | INFO
| Communications | WhatsApp group to be set-up with all committee members | EH |  | Closed
| Covid 19 | Hotel to provide hand sanitiser stations | KS | Hotel confirmed that non branded handsanitiser will be at every table. | Closed
| Covid 19 | Covid 19 certs and id to be checked at registration. | KS | Hotel will provide 2 x scanners. All attendees to have ticket and ID ready for scanning. Only scanned people will be given a name badge - Hotel have advised. ID must match name on the ticket - Hotel have advised. | 2021-11-19 | INFO
| Covid 19 | Person to be nominated to wipe down surfaces at podium between speakers. Shada to nominate and advise one of the students. | SW | Sahada to nominate graduate - meet at 19.30 on 25TH | 2021-11-09 | OPEN
| Covid 19 | All delegates to be advised of Covid 19 protocul at the start of the event | Valerie /RO'C | RO'C - to be the go to person on the day for all attendees. COVID Hi-Viz suggested as an option | 2021-11-26 | OPEN
| Covid 19 | All sponsors to have covid certs | EH | Closed - Sponsors are aware of this and will be checked on the day | 2021-11-26 | INFO
| Covid 19 | Update Covid strategy document with Richard. Updated draft prepared by Majella. | SW/KS/RO'C | When can masks be removed When seated? When must masks be kept on When not seated in your pod? When networking How is coffee break to be addressed? Richard will police. Hotel Eventbrite link to be sent by Jennifer for completion by PDA in advance of event - name on ticket must match attendee. Hotel policy - keep masks on when not seated. Hotel can provide takeaway cups to allow people to bring tea/coffee nback to their tables | 2021-11-23 | OPEN
| Covid 19 | Call with Shada Galway ATMP event | SW/KS/RO'C | They checked the certs at the beginning, mask were compulsory in the hotel, but ppl tend to take them off during talks Social distancing was partially in place. Follow-up call with NIBRT attendees to be set-up | Closed | N/A
| Covid 19 | Send email to all speakers 22 Nov - on how to get there and Covid policy | KS |  | 2021-11-22 | OPEN
| Covid 19 | All attendees, presneters, students and sponsors will need to bring proof of vacination and id - TO BE CHECKED AT REGISTRATION | SW/RO'C | No pass - no entry - reminder to be sent by Shada the week of the event. | 2021-11-26 | OPEN
| Covid 19 | Space out speakers at the event on podium? Hotel policy - face masks can only be removed when you are seated. | AK/RO'C | 6 mics - top table including VM - 2/table, 1 at lecture, Jonny will communicate Valerie via mic as back-up. Mic required for Jonny. Jennifer to allow for social distancing at podium. Other presenters can sit at their tables when they are not involved in a session. | 2021-11-25 | OPEN
| Covid 19 | Agree maximum number of people on the podium | KS/RO'C | Consider - having only the session speakers on the podium. 4 x presenter slots on podium. Agreed. Closed | Closed | N/A
| Covid 19 | Print out attendee list - with names and contact numbers - for sign-in on the day | SW | Three days before event | 2021-11-23 | OPEN
| Covid 19 | Late arrivals - how are they handled? How do we ensure that they have been checked | RO'C | Registration desk will be manned all day. Richard has the final say on the day. If you do not have a name badge - you have not been checked for covid complaince and will not be allowed to access the event - name badges must be worn at all times and be clearly visible. | 2021-11-26
| Covid 19 | Use of paper handouts at the event - Covid compliance | RO'C | closed - not applicable | Closed | N/A
| Covid 19 | Are barriers required at registration? | RO'C | closed - no not applicable | Closed | N/A
| Flowers | 2 x Flower arrangements | Kevin | Ordered and paid for. KS to collect 25 Nov | 2021-11-25 | OPEN
| Graduates | 2 x graduates to suppor the event. Meeting with graduates to be set-up in advance of the event | SW/EH/AK | Meeting date to be fixed | 2021-11-05 | OPEN
| Graduates | Graduate names and contact detials required | SW |  | 2021-11-19 | OPEN
| Hotel | Hotel - food order | EH | Elizabeth to advise the Hotel of final numbers for food - 23 Nov | 2021-11-23 | OPEN
| Hotel | Some Committee members to meet at CP to set-up the evening before the event. Dinner will also be provided - all welcome. | EH | EH/AK/SW/KS/JP/VM - confirmed - | 2021-11-25 | OPEN
| Hotel | PDA cake to be ordered | EH |  | Closed | N/A
| Hotel | On the day - Hotel contact person details required - Sean O'Neil will be there from 7.00am will be there. Can set-up 16.30 - tbc by Jennifer on Tuesday | EH |  | 2021-11-23 | INFO
| Hotel | Private room to be booked for interviews and storage | EH | Closed | Closed | CLOSED
| Hotel | Paper, pens for tables - Hotel wil supply pens, paper and water | KS |  | 2021-11-19 | INFO
| Hotel | Who is staying in the hotel overnight - presenters, VIP's, delegates, sponsors | EH | NOT OF INTEREST - closed |  | CLOSED
| Hotel | Advise Hotel of final numbers in advance of the event | EH/KS | Three days before event | 2021-11-22 | OPEN
| Hotel | Set-up in Crowne Plaza - 16.30, 25 Nov - Aga - will be there. | EH | EH, KS. SW - will be there from 16.30 | 2021-11-25 | OPEN
| Hotel | Get attendee list frorm Shada : upload on drop box - delegates (remote/present), sponsors, AVS. Presenters, committee members, graduates | SW/EH | 43 attendees, 12 speakers, 10 committee members, 2AVS | 2021-11-23 | OPEN
| Marketing | KS to prepare four quesitons for Frank to pose at KS interview - ATMPS | KS |  | 2021-11-19 | OPEN
| Marketing | Email updated agenda to Ana Collins (IPS) | KS |  | 2021-11-22 | CLOSED
| Marketing | Committee members requested to like, comment on and share LinkedIn event marketing material | All |  | 2021-11-22 | OPEN
| Marketing | Balloons to be ordered | EH | Closed | n/a | CLOSED
| Marketing | PDA promotional material for the event | EH |  | 2021-11-19 | INFO
| Marketing | Sponsor slide required | EH | Closed | 2021-11-19 | OPEN
| On the day | Roles and responsibilities on the day | All | JP/AK/MMc - mangement of virtual event - Back-up? AK - Management of AVS - Back-up? SW/2xStudents - registration desk - Back-up? EH+1 - management of photographer, journal personnel - runner required. RO'C - Management of Covid compliance - Back-up? KS - Roving mikes with AK - Back-up? Majella - remote monitoring of event will liaise with Jonny P. Back-up? Valerie - Chair, Back-up? We need named back-ups for all of the above in case they are not available on the day due to Coivd, travel restrictions, etc. | 2021-11-24 | OPEN
| On the day | KS to prepare thank-you closeout - thank committee, presenters, delegates. | KS |  | 2021-11-19 | OPEN
| On the day | KS to present gifts to xxxx | KS |  | 2021-11-19 | OPEN
| Presenters | Bios, photos and presenation summaries required from all presenters | RO'C | KS to get this information and send to Shada | 2021-11-22 | OPEN
| Presenters | Mobile numbers required for all presenters | KS | KS to get this information and share with the committee | 2021-11-19 | OPEN
| Presenters | Kate Colemam to present solo. | KS/SH | KS to get presentation topic etc from Kate. Agenda to be updated. | 2021-11-23 | OPEN
| Presenters | All vendor presentations to be loaded onto dropbox | RO'C |  | 2021-11-22 | OPEN
| Presenters | Christian's presentation to be pre-recorded and loaded onto sharepoint | AK | Christian will provide his slide deck on Mon 22nd Nov and carry out his pre-recording on Wed 24th Nov. The dry run will be carried out with Christian on Thurs 25th Nov with Alan Sullivan’s team (AVS) from the hotel one the AV equipment is set-up. AK will be present on Thurs at the hotel for this. Alan Sullivan (AVS) has been notified on the above dates | 2021-11-24 | OPEN
| Presenters | Confirm that Ann is available to open the event with Valerie | KS |  | Closed | CLOSED
| Presenters | Q&A session questIons to be requested from all speakers and shared with the committee. | KS | Request sent to all presenters: Brian - Questions recd Gary - Questions recd Aidan/Bertie - not recd Kate - not recd Warren/Kevin - not recd Christian - not recd Niall - not recd Catherine - not recd | 2021-11-19 | OPEN
| Presenters | Gifts for speakers to be ordered | EH |  | Closed | CLOSED
| Presenters | Back-up speaker | AK | Tom Bannon (PM) attending the event - will be back-up presenter | Closed | CLOSED
| Presenters | Q&A session - agree format - follow-up with Kate and Aidan | KS | Valerie will chair the Q&A sessions | 2021-11-19 | CLOSED
| Presenters | Follow-up with Richard - presentations status | KS |  | 2021-11-19 | CLOSED
| Printing and materials | Name badges for delegates | Lynn |  | 2021-11-19 | INFO
| Printing and materials | Material to be printed off for issue to each delegate - delgate list, agenda, | SW/RO'C |  | 2021-11-19 | OPEN
| Printing and materials | PDA promotional handouts | EH |  | 2021-11-25 | OPEN
| Registartion | Registration table - 3 x people required - Names required | SW | 2 x students plus Shada | 2021-11-23 | OPEN
| Registration | Smart devices required at registration | KS | Hotel will provide scanner. | 2021-11-25 | Closed
| Printing and materials | Delegate list to be shared with the committee members | EH | Closed | Ongoing | OPEN
| Registration | Place names on each table - Lunch and conference | EH/KS | not required | Closed | CLOSED
| Registration | Two x presenter tables required | EH | Closed | Closed | CLOSED
| Registration | Table plans to be printed fro all tables - conference, meals, presenters podium | KS/EH | Not applicable - people will sit where they wish to. Closed | Closed | CLOSED
| Registration | Lyn is making up name badges for all attendees | Lynn/EH |  | 2021-11-25 | OPEN
| Registration | Bring PDA membership badges | All | EH will provide replacements if you ask her. | 2021-11-26 | INFO
| Dropbox | All materials to be loaded onto dropbox - all committee members to have access | All |  | 2021-11-19 | INFO
| Sponsors | Sponsor meeting to be arranged | EH |  | Closed | CLOSED
| Sponsors | Sponsor handouts for tables | EH |  | 2021-11-25 | INFO
| Sponsors | Sponsors to set-up in Hotel day before the event | Sponsors | Closed - Sponsors are aware of this. Can set-up from 6.00pm on 25th. | 2021-11-25 | INFO
| Covid 19 | Majella to provide HSE covid update |  |  | 2021-11-23 | OPEN
| GDPR | Camera team and video will be recored at the event. All delegates to be informed by Valerie on the day. Advance notice of thei to be provided to all delegates. | VM/SW | Kate Coleman may also record - EH to follow-up with Kate | 2021-11-19 | INFO
| Marketing | Mark Barker = Publication - interviews on the day |  | EH to provide more details | 2021-11-19 | OPEN
| Marketing | Conference takeaways | KS | KS will complie this | 2021-11-26 | OPEN

## Item
Item
Flowers
Hotel
Sponsors
Presenters
Laptops
Registration
Audio/Visual
Hotel
Agenda
Printing and materials
Attendees
Dropbox
Graduates
GDPR
Marketing
On the day
Covid 19